## logbook Member 3
Date | Member | Task | Man-Hour | Output | Problem | Next Action
2026-06-23 | M3 | Set up project repo structure — configs | docs | per-member instruction guides | 2 | config/classes.yaml + 4x memberN_data.yaml + docs/project_plan.md
2026-06-23 | M3 | Scaffolded Flask backend (app.py + pipeline.py) with /health /recommend /infer | 2 | backend/ with graceful 503 until models exist; /health + /recommend verified | /infer blocked until trained weights exist | Train YOLO models
2026-06-23 | M3 | Scaffolded Flutter mobile app (camera → /infer → overlay) | 1.5 | mobile_app/lib/ (7 Dart files) | flutter create . not run yet (needs Flutter SDK) | Run flutter create . to generate Android/iOS platform folders
2026-06-23 | M3 | Set up GPU training environment; verified CUDA + smoke test | 1.5 | torch 2.6.0+cu124 + ultralytics 8.4.75 on RTX 3050; smoke-test training confirmed GPU | SSL inspection (CRYPT_E_NO_REVOCATION_CHECK) blocks ultralytics auto-download | Use curl --ssl-no-revoke helper (download_weights.py) for all weight fetches
2026-06-24 | M3 | Downloaded 4 online datasets (manhole/obstacle/wires/branches); converted COCO→YOLO; handled polygon labels | 3 | data/member3/ with 2956 images + 5899 boxes across 5 classes | wires-gklgc was COCO not YOLO; obstacle dataset had polygon labels mixed in | Created coco_to_yolo.py converter + polygon→bbox fallback in prepare_dataset.py
2026-06-24 | M3 | Initial member3 YOLO training (yolov8n 100 epochs) | 1 | mAP50=0.57; dangling_wire mAP50=0.282 (only 27 wire images) | dangling_wire severely underrepresented | Add wires2 dataset and retrain
2026-06-24 | M3 | Added wires2 dataset (1419 wire images after remap); retrained member3 | 2 | mAP50=0.675; models/member3.pt (6 MB) | Training process hung once (background task killed); relaunched via D:\mlenv | Evaluate per-class metrics; hand off training notebook to M1/M2/M4
2026-06-24 | M3 | Added member4 architecture (5 overlap classes; feature vector 57→70 dims) | 1.5 | config/classes.yaml + config/member4_data.yaml + docs/instructions_member4.md; feature_dim=70 verified | All 5 M4 classes need own photos (no public datasets except fallen_branch) | M4 to collect 80+ images/class; M3 waits for all 4 .pt files before meta-classifier
2026-06-24 | M3 | Ran member3 validation — per-class mAP50 recorded | 0.5 | uncovered_manhole=0.987, dangling_wire=0.473, obstacle_on_walkway=0.534, fallen_branch=0.685; all=0.670 | dangling_wire still weakest (0.473) — needs more data or augmentation | Consider targeted augmentation for dangling_wire; document in report §9
2026-06-27 | M3 | Retrained member3 with yolov8s (larger model) — 100 epochs | 1.5 | mAP50=0.702 (best epoch 87); models/member3.pt updated (22 MB) | yolov8s restarts epoch counter when resumed from checkpoint (no --resume flag passed) | Use last.pt with resume=True flag if retraining again
2026-06-27 | M3 | Received and integrated .pt files from M2 and M4; verified class mappings | 0.5 | models/member2.pt (84 MB pothole/dangling_wire/broken_bench/panel/socket) + models/member4.pt (6 MB Branch/Bench/shelter/socket/drainage) both load OK | member1 and member4 class-id order in config/classes.yaml did not match trained model .names (Roboflow alphabetised on export) | Fixed config/classes.yaml local id order for member1 + member4; all 20 local→global mappings verified correct
2026-06-27 | M3 | Built meta-classifier training dataset and trained meta-classifier | 2 | features.npz: 969 samples dim=70 from 575 member3 val images; meta_classifier.pt val_acc=97.9% (80 epochs) | Dataset only covers 5/11 global classes (M2/M4 val data not yet available — demo-grade only) | Collect shared annotated validation set covering all 11 global classes; rebuild features.npz + retrain meta-classifier
2026-06-27 | M3 | Redesigned Flutter app UI — Field Instrument HUD aesthetic | 3 | mobile_app/lib/theme.dart + widgets/hud.dart + widgets/hazard_card.dart; detection_painter.dart + camera_screen.dart restyled; flutter build web verified exit 0 | Google Fonts (Chakra Petch + JetBrains Mono) must be declared in pubspec.yaml before use | Wire GEMINI_API_KEY in backend for live LLM recommendations; end-to-end test on physical device
2026-06-27 | M3 | Merged M1/M2/M3/M4 val sets and retrained meta-classifier on full dataset | 1.5 | features.npz rebuilt with 1041 images (1779 boxes); meta_classifier.pt retrained: val_acc=88.5% across 10 classes (missing_barricade absent) | Dataset imbalance: dangling_wire dominates (46%); rare classes underrepresented | Per-class per-member metrics for report; baseline vs fusion ablation experiment (§10.2)
2026-06-27 | M3 | Wrote technical report (13 sections) — architecture through limitations and future work | 2 | docs/technical_report.md + docs/technical_report.docx (23 KB); 412 paragraphs, 11 tables, 13 H1 sections, 22 H2 subsections | Report complete but [M1/M2/M4] training numbers (§4.1, §5.1) marked for team to fill in | Collect M1/M2/M4 training image counts, backbones, epochs, batch sizes, mAP50/95 scores
2026-06-27 | M3 | Wrote project proposal (7 sections) — classes through deliverables | 1 | docs/project_proposal.md + docs/project_proposal.docx (15 KB); covers zone definition, class table, member roles, overlap matrix, 4 relationship types, backend vs on-device decision, 7-stage pipeline diagram | None | Report and proposal ready for review; awaiting M1/M2/M4 numbers and teammate val sets for final report fill-in
2026-06-27 | M3 | Started Flask backend for testing; verified all 5 models load and pipeline_ready=True | 0.25 | backend/app.py running on 192.168.1.5:5000; /health confirmed pipeline_ready: True; tablet can reach backend over LAN | N/A | Device demo: tap Detect on Android tablet → send frame to /infer → draw severity-coloured boxes + hazards sheet

## logbook Member 1
Date | Member | Task | Man-Hour | Output | Problem | Next Action
2026-06-23 | M1 | Set up Roboflow project and defined 5 hazard classes (pothole, open-drain, uncovered-manhole, obstacle-on-walkway, cracked-pavement) | 3 | per-member instruction guides | 2
2026-06-23 | M1 | Sourced and forked datasets from Roboflow Universe for each class | 2 | backend/ with graceful 503 until models exist; /health + /recommend verified | /infer blocked until trained weights exist
2026-06-23 | M1 | Cleaned and fixed messy class labels (renamed number labels to proper class names) | 1.5 | mobile_app/lib/ (7 Dart files) | flutter create . not run yet (needs Flutter SDK)
2026-06-23 | M1 | Merged all datasets into one project and generated final dataset version in YOLOv8 format | 1.5 | torch 2.6.0+cu124 + ultralytics 8.4.75 on RTX 3050; smoke-test training confirmed GPU | SSL inspection (CRYPT_E_NO_REVOCATION_CHECK) blocks ultralytics auto-download
2026-06-24 | M1 | Fixed data.yaml paths in Google Colab | 1 | data/member3/ with 2956 images + 5899 boxes across 5 classes | wires-gklgc was COCO not YOLO; obstacle dataset had polygon labels mixed in
2026-06-24 | M1 | Trained YOLOv8n model for 50 epochs, batch size 16, image size 640 using Tesla T4 GPU | 1 | mAP50=0.57; dangling_wire mAP50=0.282 (only 27 wire images) | dangling_wire severely underrepresented
2026-06-24 | M1 | Model achieved mAP@0.5 = 0.7141 and mAP@0.5:0.95 = 0.4618 | 2 | mAP50=0.675; models/member3.pt (6 MB) | Training process hung once (background task killed); relaunched via D:\mlenv
2026-06-24 | M1 | Shared best.pt and validation set with team leader for meta-classifier integration | 0.5 | config/classes.yaml + config/member4_data.yaml + docs/instructions_member4.md; feature_dim=70 verified | All 5 M4 classes need own photos (no public datasets except fallen_branch)

## logbook Member 2
Date | Member | Task | Man-Hour | Output | Problem | Next Action
2026-06-23 | M2 | Reviewed project requirements and planned Member 2 tasks. Identified five hazard classes and YOLO workflow. | 1 | Defined Member 2 scope and class list. | Defined the project scope and assigned five hazard classes to Member 2. | Collect datasets for the assigned hazard classes.
2026-06-23 | M2 | Collected pothole images from Roboflow and Kaggle. Verified annotations and removed unsuitable samples. | 2 | Initial pothole dataset prepared. | Limited public datasets were available for some hazard classes. | Continue collecting the remaining hazard classes.
2026-06-23 | M2 | Collected dangling wire, broken bench, broken shelter panel and exposed socket images from public sources. | 3 | Raw datasets for all five classes collected. | Images from different sources had inconsistent quality and formats. | Verify annotation quality and dataset consistency.
2026-06-23 | M2 | Reviewed datasets in Roboflow. Corrected labels and checked class mapping for Member 2. | 1 | Dataset cleaned and annotations verified. | Several annotations required correction to match the assigned class IDs. | Export the dataset in YOLO format.
2026-06-24 | M2 | Prepared YOLO train and validation datasets. Merged datasets and verified member2_data.yaml. | 3 | Training and validation datasets prepared successfully. | Dataset structure and image-label pairs required verification before training. | Configure the YOLOv8s training environment.
2026-06-24 | M2 | Configured YOLOv8s notebook and attempted local training on RTX 4050. | 1 | Initial training environment configured successfully. | Initial local training encountered dependency and environment configuration issues. | Monitor the initial training performance.
2026-06-24 | M2 | Encountered CUDA errors on RTX 4050. Investigated environment and dependencies. | 2 | CUDA issue identified and troubleshooting completed. | CUDA illegal memory access and GPU instability interrupted local training. | Continue training using Google Colab.
2026-06-24 | M2 | Moved training to Google Colab and resumed training from checkpoint. | 4 | Google Colab GPU environment configured successfully. | Local GPU crashes required migration to Google Colab and checkpoint recovery. | Complete the remaining training epochs.
2026-06-24 | M2 | Completed YOLOv8s training and evaluated the model. | 0.5 | YOLOv8s model trained and evaluation completed. | Model performance for several minority classes required further evaluation. | Evaluate the trained model and save the best checkpoint.
2026-06-27 | M2 | Prepared validation outputs and exported best.pt for the meta-classifier. | 1.5 | best.pt, confusion matrix and validation metrics generated. | Model checkpoint and validation outputs required verification before sharing. | Share the validation dataset with the meta-classifier team.
2026-06-27 | M2 | Completed report sections covering dataset collection, annotation, training configuration and evaluation. | 0.5 | Project report updated with training configuration and results. | Training results and performance metrics needed to be summarized for documentation. | Finalize the report and supporting figures.
2026-06-27 | M2 | Prepared validation images and labels for meta-classifier integration. | 2 | Validation dataset packaged for meta-classifier integration. | Validation images and labels required organization before sharing with teammates. | Verify the integrated dataset with teammates.
2026-06-27 | M2 | Verified final model performance and summarized Precision, Recall, mAP@0.5 and mAP@0.5:0.95. | 1 | Final evaluation completed (Precision 0.533, Recall 0.509, mAP@0.5 0.505, mAP@0.5:0.95 0.270). | Model performance was verified to ensure the required mAP@0.5 target was achieved. | Submit the final model and evaluation results.
2026-06-27 | M2 | Reviewed project documentation and finalized Member 2 deliverables. | 1 | Project deliverables reviewed and finalized. | All project deliverables were checked for completeness before submission. | Submit the completed project for evaluation.

## logbook Member 4
Date | Member | Task | Man-Hour | Output | Problem | Next Action
2026-06-23 | M4 | Collected initial datasets from Roboflow Universe and personal photographs for Member 4 hazard classes | 2 | Initial dataset compiled for all five classes | Public datasets contained inconsistent class names and extra labels | Standardize labels and remove unnecessary classes
2026-06-23 | M4 | Cleaned and relabelled dataset in Roboflow to match project class definitions | 2 | All labels renamed to project classes; unused classes removed | Manual relabelling required for many annotations | Generate a new dataset version and verify class mappings
2026-06-23 | M4 | Generated Roboflow dataset version and exported YOLOv8 dataset for training | 1 | Dataset Version 3 exported with five project classes | Validation split did not contain Branch annotations | Improve dataset split and regenerate dataset version
2026-06-23 | M4 | Performed first YOLOv8n training (100 epochs) on Google Colab | 2 | Model trained successfully; overall mAP50 ≈ 0.598 | Branch class absent from validation set, reducing evaluation reliability | Improve dataset balance and validation distribution
2026-06-24 | M4 | Improved dataset by adding additional images and regenerating Roboflow Version 4 | 2 | Better class balance and corrected validation split | Required additional annotation and verification | Retrain YOLO model using updated dataset
2026-06-24 | M4 | Retrained YOLOv8n model using updated Version 4 dataset (60 epochs) | 2 | Precision = 0.783, Recall = 0.541, mAP50 = 0.615, mAP50-95 = 0.339 | Broken Bench remained the weakest-performing class | Continue training to 100 epochs and compare performance
2026-06-24 | M4 | Completed final YOLOv8n training (100 epochs) using updated dataset | 2 | Final model (best.pt) achieved Precision = 0.682, Recall = 0.576, mAP50 = 0.598, mAP50-95 = 0.337 | Minor performance fluctuation compared with 60-epoch run due to training randomness | Finalize model and distribute best.pt to team members
2026-06-24 | M4 | Verified trained model and prepared deployment artifacts | 1 | best.pt exported successfully and shared with project leader for integration | None | Integrate model into multi-model hazard detection pipeline